## task list
Line Item | Line Item -- Description | Mockup | Markup | Development | Notes
Week 1 | Milestone 1 Start – Calculus I
1.1 | Initial Project Setup and build tools (Haskell) | n/a | n/a | Not Completed
1.2 | Project scaffolding and utility functions | n/a | n/a | Not Completed
1.3 | Write a context free grammar for simple infix expression in LaTeX. This will be used to evaluate definite integrals. | n/a | n/a | Not Completed
1.4 | Write a context free grammar for basic integrals in LaTeX. (Math 75 concepts). This will be what the actual input consists of. | n/a | n/a | Not Completed
1.5 | Implement an interpreter using the recursive decent pattern for the grammar defined for simple infix expressions | n/a | n/a | Not Completed
1.6 | Implement an interpreter using the recursive decent pattern for the grammar defined for basic integrals | n/a | n/a | Not Completed
Week 4 | Milestone 1 Delivery
Week 4 | Milestone 2 Start -- Calculus II
2.1 | Extend the context free grammar defined from the previous milestone to include concepts from (Math 76) | n/a | n/a | Not Completed
2.2 | Extend the interpreter built in the last milestone so that it now interprets the new grammar that has been defined in this milestone | n/a | n/a | Not Completed
2.3 | Build out the presentation layer using MathML and parses the input and output to display the respective equations that were entered | n/a | n/a | Not Completed
Week 8 | Milestone 2 Delivery
Week 8 | Milestone 3 Start -- UI
3.1 | Mock up the landing page: where users will first arive to the web page. This isn't isn't an actual separate page but rather something you will close that will explain the interpreter and how to use it. | Not Completed | n/a | n/a
3.2 | Mock up the calculation page: similar to wolfram alphas calculation page. Needs to allow for input and display input and output equations | Not Completed | n/a | n/a
3.3 | Mark up the landing page: have the landing page transistion into the calculation page without a page refresh. | n/a | Not Completed | n/a
3.4 | Mark up the calculation page: display the MathML output and the interpreter output as well as implement the designs | n/a | Not Completed | n/a
3.4 | Implement an API endpoint that communicates with the Haskell interpreter or invokes the Haskell interpreter and returns the output and formats the MathML | Not Completed | Not Completed | Not Completed
Week 12 | Milestone 3 Delivery
Week 12 | Milestone 4 Start -- Calculus III
4.1 | Extend the context free grammar defined from the second milestone to include concepts from (Math 77) | n/a | n/a | Not Completed
4.2 | Extend the interpreter built in the second milestone so that it now interprets the new grammar that has been defined in this milestone | n/a | n/a | Not Completed
Week 16 | Milestone 2 Delivery